## Slide 1: National Viral Hepatitis Control Program SDG goal 3.3 to ….combat viral hepatitis
Program launched by the Hon’ble HFM in July, 2018
Laboratory and treatment guidelines along with operational guidelines were released
Free treatment for Hepatitis B included in addition to Hepatitis C – February, 2019
Launch of MIS portal for paperless recording & reporting of data & the national helpline (1800-11-6666) in July, 2019

## Slide 2: Update Till Date
435 Master Trainers trained at National level for diagnosis, management and M&E across the country.
Treatment services started in 19 states in model treatment centres (MTC)
53,390 have been screened for hepatitis C
19,997 patients have been put on treatment for hepatitis C
Two sensitization workshop for state nodal officers & two rounds of Video Conference for monitoring held
Steering Committee & Injection safety Committee revised

## Slide 3
Activities | Status | Request to states
State Viral Hepatitis Management Unit | Established : 31 states Pending in – MP, A&N Islands, Chandigarh, D&NH and Daman & Diu | Establish in the remaining states/UTs by 30.09.2019.
State Steering Committee | Established : 26 states Pending in – Goa, MP, Mizoram, Uttarakhand & all UTs | Establish in the remaining states/UTs by 30.09.2019.
Model Treatment Centre/Treatment Centre | MTCs Established in 19 states – 21 functional (Annexure – 1 ). TCs functional in 79 districts – Completed – Punjab(26/26), Haryana(22/22), J&K (8/8) Partial – Odisha (14/33), Uttarakhand(5/16) | Start MTCs by 30/09/2019 Start all TCs (at least 1 in every district) by 31/03/2020.

## Slide 4
Activities |  | Status | Request to states
Training Progress | Medical Officers | Training Completed: 18 States | Complete all trainings by 31.10.2019
 | Lab Tech | Training Completed: 15 states | 
 | M& E Portal | Training Completed: 10 states Bihar, Goa & Sikkim have done only for M&E | 
Immunization of Health Workers |  | Completed in Himachal & Maharashtra Started in Gujarat, Mizoram, Tamil Nadu & Telangana | Complete by 31/03/2020 Vaccine from RI Syringes – local procurement

## Slide 5: Request to States
Prepare for starting Hepatitis B management services in December 2019.
Accord wide publicity to the national helpline (1800-11-6666)
100% cash grant has been released.
  Open child accounts at all level (as per practice in state)
  Transfer funds to Programme.
States may enter into rate contracts for up to 25% of their annual requirements of drugs and kits; and procure the drugs and kits
  Avoid stock outs
  Specifications shared.
  Funds may be used from cash grant or free drugs\diagnostics.
Screen all high risk populations in 2019-20 in campaign mode.